## Sheet1
Task Name | Start | End | Duration (days)
Info Seeking | 2016-09-07 | 2016-09-14 | 7
Dataset Choosing | 2016-09-14 | 2016-09-21 | 7
Work Plan | 2016-09-28 | 2016-10-05 | 7
Understanding the research questions and statistically representing it. | 2016-10-05 | 2016-10-12 | 7
Finding required and redundant variables | 2016-10-12 | 2016-10-19 | 7
Cleaning of data and formatting it according to R requirements. | 2016-10-19 | 2016-10-26 | 7
Data Cleaning documentation draft | 2016-10-26 | 2016-11-02 | 7
Team Progress | 2016-10-26 | 2016-11-02 | 7
R Script Draft | 2016-11-02 | 2016-11-16 | 14
R Plot Draft | 2016-11-16 | 2016-11-30 | 14
Presentation | 2016-11-30 | 2016-12-14 | 14
Git Package | 2016-11-30 | 2016-12-14 | 14